## Лист1
Task | Start Date | Working days | End Date | # days | task # | Completion
Making of a Gantt Chart (Mark, Umar) | 2025-11-27 | 1 | 2025-11-28 | 2 | 1 | 100%
FREECAD Modelling (Aleksandr, Muhammadqodir) | 2025-11-27 | 4 | 2025-12-01 | 5 | 2 | 50%
Python Coding (Azimjon, Ahrorbek) | 2025-12-01 | 3 | 2025-12-04 | 4 | 3 | 70%
PPT presentation (Khayatxon, Yusuf) | 2025-11-28 | 3 | 2025-12-01 | 4 | 4 | 75%
Technical report (All team) | 2025-11-30 | 2 | 2025-12-02 | 3 | 5 | 50%
Working days
Making of a Gantt Chart (Mark, Umar) | 1
FREECAD Modelling (Aleksandr, Muhammadqodir) | 4
Python Coding (Azimjon, Ahrorbek) | 3
PPT presentation (Khayatxon, Yusuf) | 3
Technical report (All team) | 2
Formulas:
End Date = [Start Date]+[Working days]